# Development Plan - XPERIMENT_AI

## Method

I work in sprints rather than one long milestone. Each sprint has:

Goal: one sentence stating the user-visible change.

Need behind it: which stakeholder concern or previous-sprint finding triggered it.

Planned tasks: broken down to ½–1 day items.

Review (end of sprint): what worked, what didn't, what to carry forward.

Adaptation: explicit change to the next sprint's plan (scope cut, new task, dropped task).

The board itself is lightweight: a tracked text list (this document is the source of truth) plus the commit log as the time-stamped event stream. I deliberately do not use Jira / Linear for a solo project. Overhead is higher than the value at this team-size, and the commit log already gives me traceable evidence.

## Sprint timeline

| # | Dates (2026) | Goal | Status |
| --- | --- | --- | --- |
| S0 | Apr 20 – Apr 24 | Bootstrap the project skeleton and pick a stack. | done |
| S1 | Apr 27 – May 1 | First end-to-end: static deploy + Kling video gen + password gate. | done |
| S2 | May 4 – May 8 | Image generation, AI prompt enhancer, presets, audio sync. | done |
| S3 | May 11 – May 22 | History library, expanded chip vocabulary, intros editor, dev Lab. | done |
| S4 | May 25 – Jun 5 | Portfolio + session-policy tightening + polish. | in flight |
| S5 | Jun 8 – Jun 12 | Last testing and quality control. Final presentation | planned |

## Sprint records

### Sprint 0: Bootstrap (Apr 20 – Apr 24)

Sprint goal: Pick a stack and stand up a "hello world" that I can deploy without thinking about it again.

Need: I have no scaffold and no host. Without one I can't iterate on any feature.

Planned tasks

Decide between Next.js, plain static + serverless, and ASP.NET

Scaffold the Razor Pages project as the templating source.

Write a build-docs.py that flattens Razor into static HTML.

Push to GitHub, get a deploy preview.

Review. GitHub Pages worked for static, but as soon as I needed a real backend (Kling API key, KV storage) Pages was a dead end. The static-build-from-Razor idea was kept but the deploy was migrated to Vercel.

Adaptation → S1. Add "migrate to Vercel + first serverless function" as the headline of the next sprint, before any video work.

### Sprint 1: First end-to-end (Apr 27 – May 1)

Sprint goal: A logged-in user can pick chips, press GENERATE, and get a Kling-rendered video downloaded to disk.

Need: Without this loop, nothing else has a reason to exist. Every later feature plugs into it.

Planned tasks

Switch deploy from GitHub Pages to Vercel build-on-push. (commit `c855bf9`)

Implement /api/generate (Kling JWT, text2video and image2video).

Implement /api/status polling and the front-end modal that drives it.

Implement /api/download proxy (cross-origin download attribute doesn't trigger in browsers). (commits `6ac1862`, `b34a19b`)

Hard-code an operator + dev password and gate every API endpoint. (commit `ed2b924`)

Dashboard page + KV-backed chip CRUD.

Subscription page with mock plan + real stats counters.

Review. Took longer than 4 days because Kling rejected my first dozen requests for not specifying duration in their exact accepted set (5 or 10 only). Documented in the commit log. The auth gate and Dashboard turned out to be smaller than expected; serverless cold-starts were the real friction.

Adaptation → S2. Carry the "what makes a good prompt for this scene?" question into S2. The chips alone were producing technically-correct-but-bland videos.

### Sprint 2: Polish the signal (May 4 – May 8)

Sprint goal: Make the output feel on-brand, not just the UI. Add image generation as a second cheap, fast surface.

Need: Output quality complaint from the first real test session: chips produce a coherent but flat prompt; Kling needs more cinematographic language.

Planned tasks

Add BFL Flux 1.1 Pro Ultra integration (/api/image).

Add /api/enhance: Claude rewrites the assembled chip prompt into a 400–600 char cinematographer-grade paragraph. (commit `ce87840`)

Add named presets (save / recall / delete): operators iterating on a single video want this.

Add audio BPM + energy detection (browser-side) — the artist uploads the track and the prompt picks up tempo language.

Add a QUALITY chip mapping to four Kling model presets. (commit `aff6beb`)

- Review. The enhancer was the single biggest output-quality lift; presets came in second. Audio sync looked clever in demos but rarely changed the prompt meaningfully on a 5 s clip, I decided to keep it but it's at a lower-value than expected.

Adaptation → S3. Carry the audio-sync underperformance as a future cut candidate. Promote "expand the chip vocabulary" to top of the next sprint.

### Sprint 3: History, expansion, dev tooling (May 11 – May 22)

Sprint goal: The user can find what they made last time. The developer can debug without ssh-ing into Vercel.

Need: First operator session ran out of "where did that good one go?". From my own side I had no quick way to see whether KV / providers were configured correctly in a given deploy without reading the function source.

Planned tasks

/api/history + the History page (filter by image/video, viewer modal, re-render, delete).

Four new chip categories: Genre, Location, Time, Deliverable. (commit `7a22c15`)

Editable intros (the "anchor sentence" prepended to every prompt) + chip-count badges on the dashboard panels. (commit `e64bee6`)

/api/info diagnostic endpoint + the Lab page (provider status, KV state, recent renders, prompt tester, action buttons, API health pings). (commit `c4f8a83`)

Themed scrollbars (small but the bloom theme felt half-finished without it). (commit `1626f23`)

Review. The Lab page paid for itself the first time I ran it. It surfaced an xa-history key that wasn't being written because of a bad taskId dedup check, which I'd never have caught from the UI. Recent-renders showing a null model on three entries pointed me at a missing default in pollStatus.

Adaptation → S4. Move portfolio writing to the top of the next sprint (university deadline). Lower session TTL since I'm sharing the password with one more person and 30 days felt too long.

### Sprint 4: Portfolio + tightening (May 25 – June 5)

Sprint goal: Hand in a portfolio that is structured, defendable, and traceable to the artefacts in the repo. Tighten one security setting that has been bothering me.

Need: University portfolio review feedback flagged that I had decision logs but not enough structured methodology, and that designs were under-justified. Also: 30-day sessions are too generous given a hard-coded shared password.

Planned tasks

Drop session TTL from 30 days to 7.

Write four decision logs.

Write at least two documents per learning outcome.

Produce a C4 architecture diagram.

Manual end-to-end smoke test of the deployed site (image + video + auth + Lab).

Sprint review (planned): Has every LO got at least two pieces of evidence I'd be comfortable defending in person? If not, write more before submitting.

### Sprint 5: Stripe spike + multi-user prep (Jun 8 – Jun 12)

Sprint goal: Replace the placeholder Subscription buttons with a real Stripe checkout flow (test mode) and design the multi-user data model.

Need: Subscription page is the only page with mocked actions; it embarrasses every demo. And the hard-coded two-role auth is a ceiling on the user base.

Planned tasks

Stripe customer + price object in test mode.

/api/checkout + /api/webhook (Vercel raw-body handler).

Design a users KV namespace and migration plan from the current shared-password model.

Document the migration in a fifth decision log.

## Definition of done (across all sprints)

A change ships only if:

It is reachable from the deployed site (vercel.json build passes).

It does not break any other page (manual smoke test of Image + Video + Dashboard + History at minimum).

The Lab page health pings stay green.

The commit message starts with ADD:, FIX: or REMOVE: so the log is filterable later.

## How I review

End of each sprint I do a private retro: three bullets: what worked, what dragged, what to change next time. The changes get rolled into the next sprint's "Adaptation" line above, so the document itself is the audit trail.