# LO5 · Managing — Sprint cadence and control

How I planned, ran, reviewed, and adapted across the realised sprints. The intent here is to make the methodology defendable: not "I did sprints," but "here are the sprint goals, here are the changes between sprints, and here is the evidence those changes happened because of the previous sprint's review."

This document is a companion to `development-plan.md`. The plan is the timeline; this is the reasoning behind the changes between sprints.

## 1. Cadence I committed to

Sprint length: ~3 working days. Short enough that scope creep is visible the next sprint; long enough to actually ship a feature.

Each sprint has: one sentence goal, the need behind it, planned tasks, a closing review, and an adaptation that feeds the next sprint.

Definition of done: reachable from the deployed site, smoke test passes, Lab health pings green, commit message tagged.

Tooling: the development plan markdown is the board; the git log is the event stream. No Jira / Linear for a one-person team — the overhead would not pay back.

This is what "agile" means in this project: short iterations, end-of-iteration reflection, plan adjusted by what reflection found. Not the ceremony of stand-ups, sprint poker, or burndown charts — those are for teams.

## 2. Sprint-by-sprint controls

Below: the need that drove the sprint goal, the review observation, and the explicit adaptation into the next sprint. The point is that none of these adaptations were arbitrary — each has an antecedent in the previous sprint.

### Sprint 0 (May 13–14) — Bootstrap

Need: No scaffold; can't iterate on anything until something deploys.

Plan: Pick a stack; stand up Razor + a static-build path.

Review found: GitHub Pages is fine for static but a dead end for backend work; the static-build idea is good but the host is wrong.

Adapted into S1: First goal of S1 changes to "migrate to Vercel + first serverless function" before the first product feature.

### Sprint 1 (May 14–18) — First end-to-end

Need: A working Kling render is the foundation under every later sprint. Without it nothing else has a reason to exist.

Plan: Migrate deploy, implement /api/generate + /api/status, build the modal, add the auth gate.

Review found: Took 4 days, not 3. Kling's duration constraint cost half a day (commit ded23d0). The auth gate was smaller than expected; the cross-origin download proxy was a surprise piece of work. Output looked technically right but visually flat — the chips alone weren't carrying the scene.

Adapted into S2: Carry the "prompt is flat" finding to the top of the next sprint. Promote "AI enhancer + scene-specific intros" over "image generation" in priority.

### Sprint 2 (May 18–26) — Polish the signal

Need: Output quality lift, plus an image surface so the user can previs a video idea cheaply.

Plan: BFL Flux image gen, Claude enhancer, named presets, audio BPM detection, QUALITY chip mapping.

Review found: Enhancer was the biggest visible lift; presets second. Audio sync was visibly slick in demos but rarely changed output meaningfully on 5 s clips. Per-page POLL_CONFIG showed up as a design pressure during implementation and was a clean addition.

Adapted into S3: Carry the audio-sync underperformance as a future cut candidate. Promote "expand the chip vocabulary + persist history" to next-sprint top.

### Sprint 3 (May 26–28) — History, expansion, dev tooling

Need: Operators were losing good outputs ("where did that one go?"). I needed a way to inspect KV state in a given deploy.

Plan: History page + endpoint, four new chip categories, editable intros, Lab dev page.

Review found: The Lab page paid for itself on the first run — surfaced a missing taskId dedup that I would never have caught from the UI. Recent-renders showing model: null on three entries pointed me at a default that was missing in pollStatus. Bloom-theme scrollbars looked broken; small fix.

Adapted into S4: Move portfolio writing to the top of the next sprint; tighten session TTL since a second person now has the password.

### Sprint 4 (May 28–31) — *current*

Need: University portfolio deadline. Feedback flagged that the methodology and design step were under-documented. Also: 30-day sessions are too generous given a shared password.

Plan: Write the portfolio (this directory), tighten SESSION_DAYS to 7, run the smoke test end-to-end.

Review (planned, end of sprint): does every LO have ≥ 2 defendable artefacts? If not, write more before submitting.

Adaptation candidate into S5: Promote Stripe + multi-user account model, retire the shared password.

## 3. What I track during a sprint

Lightweight, by design:

The commit log. Every commit message starts with ADD:, FIX:, lab:, or similar so the log is filterable later. Looking at it now is the closest thing to a retrospective board.

A short list in this file's predecessor (`development-plan.md`). Bullet ticks as tasks land; not a separate tool.

The Lab page's API_HEALTH panel. End-of-day ping during a sprint — if anything is red, that's tomorrow's first task.

My own subjective "is this sprint losing momentum?" check at the midpoint. If yes, cut scope rather than push through.

## 4. What I do not track (and why)

Story points / velocity. Single-developer; the number is meaningless.

Burndown charts. Same reason.

Backlog grooming meetings. I groom by writing the next sprint's plan in this file at the end of the previous one. The act of writing it is the grooming.

## 5. How I adapt scope when a sprint goes sideways

There were two real cases of this:

S1 — Kling duration bug. Dropped the planned "stats counters" task one day; resumed in S2. The trade was: stats can wait, video can't.

S3 — Lab page scope ballooned. Started as "one panel: provider status"; grew to 12 panels in two days because each one surfaced an interesting failure mode. I did not stop it because the value per panel was visibly high (each one caught a bug). The cost was that I went into S4 without finishing the multi-user prep — moved to S5.

The lesson recorded in `development-plan.md`: expanding scope is acceptable if the new scope is delivering value per unit; cutting other scope to absorb it is the right move, not staying late.

## 6. Stakeholder feedback loop

In a real team this would be sprint review attendance. Here it is:

Operator (the artist's visual director) uses the tool at the end of each sprint and tells me what's broken or missing. Two of the four sprint adaptations above (S1 → S2 "prompt is flat"; S2 → S3 "where did that one go?") came directly from this feedback channel.

Me as the developer is also a stakeholder — the Lab page is for me. Adaptations driven by developer-stakeholder feedback are not less legitimate; they fund the system's long-term reliability.

## 7. Visible artefacts of management

| Artefact | Where to find it | What it shows |
| --- | --- | --- |
| The sprint timeline | `development-plan.md` §"Sprint records" | What was planned vs. what shipped |
| The decision logs | `decision-logs/` | The non-obvious choices, with criteria and verification |
| The commit log | git log --oneline | Every change, tagged for filter |
| The Lab page in the deployed app | /lab (dev login) | Health, KV state, recent renders |
| The smoke test in `LO4-realizing/02-testing-and-verification.md` | this folder | The end-of-sprint pass/fail checklist |

These are the things I'd put on a slide to defend "I ran this project with a structured methodology, not by vibes."